## Sheet1
Week | Task | Description / Goal | Deliverable | Status
1 | Refresh ML fundamentals | Review regression, classification, bias/variance, eval metrics | ml_basics.ipynb
1 | Implement regression/classification models | Practice with scikit-learn datasets | Evaluation plots
2 | Learn neural network basics | Study forward/backprop, activation functions | Notes on NN concepts
2 | Build first neural net | Train MLP on MNIST or CIFAR-10 (PyTorch/TensorFlow) | nn_classification.ipynb
3 | Study CNNs & transfer learning | Learn about convolutions & pretrained models | cnn_transfer_learning.ipynb
3 | Experiment with GPU training | Use Colab GPU, measure training time | Runtime comparison
4 | Learn NLP & transformers | Tokenization, embeddings, attention concepts | HF course Chapter 1–2
4 | Run Hugging Face model | Sentiment analysis using pre-trained transformer | nlp_transformers_intro.ipynb
5 | Explore Hugging Face ecosystem | Use datasets, Trainer, and transformers APIs | HF fine-tuned text classifier
5 | Fine-tune small model | Train classifier or QA model on toy dataset | hf_finetune_text_classification.ipynb
6 | Learn OpenAI/Azure OpenAI APIs | Generate text & embeddings | llm_embeddings_intro.ipynb
6 | Build embedding pipeline | Chunk → embed → store vectors (FAISS/Chroma) | Working embeddings code
7 | Learn LangChain fundamentals | Understand chains, agents, retrievers | LangChain notes
7 | Build RAG prototype | Use LangChain + OpenAI embeddings for Q&A | rag_langchain_demo.ipynb
8 | Design LLM system architecture | Create RAG + Analytics Assistant diagrams | ai_architecture_notes.md
9 | Learn Azure ML MLOps | Understand training → registry → endpoint flow | mlops_azureml_demo.ipynb
9 | Deploy a model in Azure ML | Use online/batch endpoint | REST endpoint tested
10 | Study NVIDIA GPU basics | GPU vs CPU, CUDA concepts | nvidia_gpu_notes.md
10 | Benchmark GPU vs CPU | Train same model on both | Runtime logs
11 | Build Capstone Project #1 | LLM + RAG + Azure project (enterprise assistant) | rag_project/
11 | Document architecture | Diagram + setup guide | README.md
12 | Build Capstone Project #2 | Classical ML + MLOps (churn prediction) | churn_mlops_project/
12 | Deploy & monitor model | Register, deploy, test endpoint | Demo screenshots/logs
12 | Polish portfolio | Push all notebooks/projects to GitHub | Updated GitHub profile
13 | Explore Databricks AI Features | Understand Databricks Lakehouse AI integration and Mr. Bricks assistant | Databricks_AI_Overview.md
13 | Hands-on with Mr. Bricks | Use Mr. Bricks for code generation, pipeline suggestions, and troubleshooting in Databricks | mr_bricks_demo.ipynb
14 | Integrate Databricks with Azure OpenAI | Build workflow using Databricks notebooks + Azure OpenAI for AI-driven data processing | databricks_openai_integration.ipynb
14 | Explore Databricks Model Serving | Deploy ML model as REST endpoint within Databricks environment | databricks_model_serving_demo.ipynb
15 | Use Databricks Unity Catalog for Governance | Implement fine-grained access control and lineage tracking using Unity Catalog | unity_catalog_governance.md
15 | Implement Databricks Feature Store | Create and manage reusable ML features for training and inference | feature_store_demo.ipynb
16 | Capstone Project #3 – Databricks AI Integration | Build end-to-end pipeline combining Databricks, Azure OpenAI, and Mr. Bricks assistant for automated data curation and insights | capstone_databricks_ai_project/
16 | Document and Present Final Portfolio | Summarize all 4 months of learning, prepare for AI Architect interviews | portfolio_presentation.md